## Sheet1
Task	Start Date	End Date	Duration
Project Planning	9/1/2022	9/8/2022	7
Project Proposal and Submission	9/8/2022	9/18/2022	10
Research and Requirement Analysis	9/19/2022	10/5/2022	16		44805	44923
Understanding IOT concepts	9/5/2022	10/14/2022	39
Gather software and hardware requirements	9/15/2022	10/30/2022	45
Design the prototype for Anti-theft security system	10/19/2022	11/7/2022	19
Develop the hybrid mobile application using React Native	10/8/2022	11/26/2022	49		44805	44923
System Testing	11/27/2022	12/7/2022	10
Dissertation Report	10/5/2022	12/30/2022	86
Feedback Analysis	11/30/2022	12/28/2022	28